## Sheet1
Start Date | Duration (Weeks) | Due Date | Completed | Task | Phase | Notes
2023-10-25 | 1 | 2023-11-01 | 2023-10-26 | Create user stories | Planning
2023-11-01 | 2 | 2023-11-15 | 2023-11-01 | Create project skeleton - HTML and CSS | Design / Coding
2023-11-15 | 1 | 2023-11-22 | 2023-11-18 | Use Udemy course to learn CSS Methodologies | Research
2023-11-15 | 1 | 2023-11-22 | 2023-11-18 | Use Udemy course to learn Javascript ES6 | Research
2023-11-15 | 1 | 2023-11-22 | 2023-11-15 | Create wireframe diagrams to show skeleton structure of the webpage | Design
2023-11-15 | 2 | 2023-11-29 | 2023-11-19 | Create UML Diagrams to represent relationships between objects | Planning
2023-11-15 | 2 | 2023-11-29 | 2023-11-15 | Decide on most appropriate database format; json or sql .db | Design
2023-11-15 | 2 | 2023-11-29 | 2023-11-18 | Modify HTML/CSS skeleton with 'media queries' to improve webpage responsiveness, as per "08-Design\Design.md" | Coding
2023-11-15 | 2 | 2023-11-29 | 2023-11-18 | Modify HTML skeleton code to follow Bootstrap or Grid framework | Coding | Project structure fits uses Flexboxes to meet RWD requirements
2023-11-15 | 1 | 2023-11-22 | 2023-11-15 | Implent an "Ultrawide" layout, displaying all three sections in a single row using flexboxes. Create relevant wireframe diagrams. | Design / Coding
2023-11-22 | 1 | 2023-11-29 | 2023-11-22 | Implement a prototype of the View Page JavaScript to take test JSON data and display as a table | Coding
2023-11-22 | 2 | 2023-12-06 |  | "Prettify" the above table; CSS | Design / Coding
2023-11-29 | 2 | 2023-12-13 |  | Implement the HTML form to add new items to a JSON database | Coding
2023-11-29 | 2 | 2023-12-13 |  | Update view.js to read and parse data from the real JSON database | Coding
2023-12-13 | 5 | 2024-01-17 |  | Investigate SQL / PostgreSQL as a relational database as opposed to JSON; check this fits CW limits? | Research
2023-12-13 | 5 | 2024-01-17 |  | Create "Interim Video" | Documentation
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
| 2 | 1900-01-13
Formulas:
Due Date = [Start Date]+([Duration (Weeks)]*7)